## Schedule
ID | Task Name | Most Likely Duration | Predecessors | Min Duration | Max Duration | Outline Level | Summary | Distribution Type
1 | Design development | 5 |  | 4 | 7 | 1 | FALSE | triangular
2 | Client design approval | 3 | 1FS | 2 | 6 | 1 | FALSE | pert
3 | Order cabinets | 4 | 2FS | 3 | 8 | 1 | FALSE | uniform
4 | Demolition | 3 | 2SS+1d | 2 | 5 | 1 | FALSE | triangular
5 | Rough plumbing | 4 | 4FS | 3 | 7 | 1 | FALSE | pert
6 | Rough electrical | 3 | 4FS | 2 | 5 | 1 | FALSE | normal
7 | City inspection | 2 | 5FS,6FS | 1 | 5 | 1 | FALSE | triangular
8 | Install cabinets | 5 | 3FS,7FS | 4 | 8 | 1 | FALSE | uniform
9 | Flooring and paint | 4 | 7FS | 3 | 6 | 1 | FALSE | pert
10 | Install appliances | 2 | 8FS,9FS | 1.5 | 4 | 1 | FALSE | lognormal
11 | Test and commission | 1 | 10FS | 0.75 | 2 | 1 | FALSE | normal
12 | Project turnover | 0 | 11FS | 0 | 0 | 1 | FALSE | triangular